| Project: UConnect at UCAR |  | Project Manager: T. Eastburn |  |  |  |  | September 2013 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| UConnect at UCAR Scope Statement |  |  |  |  |  |  |  |
| A visible and unified online education and outreach effort that leverages and expands upon existing and newly developing efforts throughout the organization to deliver, coalesce and archive UCAR knowledge and educational assets. It will be designed to ensure intuitive accessibility for all audiences, be thematically based, and leverage social media and other evolving technologies, services, and utilities whenever possible to ensure a robust and thriving online center of excellence in the atmospheric and related sciences that shares knowledge and builds collaboration with key stakeholders. |  |  |  |  |  |  |  |
| Objectives/Deliverables |  |  |  |  |  |  |  |
| Statement: Development of deliverables will provide free and open access to UCAR knowledge assets including events (colloquia, seminars, talks), expertise (videos, webinars), and resources (COMET, Spark Teaching Boxes, COMET modules…). |  |  |  |  |  |  |  |
| Highest Priorities - UConnect Website (Phase I: Nov. Dec. Jan.) and UConnect YouTube Channel: Nov. 11 - Editorial calendar: Professionally produced videos, 8-10 annually, on topics of relevance and of value to our stakeholders - Video interviews providing QA with scientists – (often post webcasts and/or webinars, Subject Matter Experts) – (i.e. Meehl, Trenberth thus far) - Teaching Boxes, each summarized via a short video introduction, and placed in a meaningful context for K-12 educators (Draft of Clouds thus far) - Higher Ed Topical Teaching Boxes across key content areas and needs within the atmospheric Sciences (Division of Planetary Science model) Secondary Priorities - Webcasts of colloquia, seminars, workshop sessions/series through live video streaming - Video repository development for media’s use - Judicious selection of webinar delivery platform that meets our highest standards and needs - Judicious selection of high-level webinars to occur monthly to quarterly (4-6x annually) - Asynchronous archiving of high-level webinars for UCAR stakeholders - Asynchronous archiving of selected webcasts on UConnect at UCAR’s YouTube channel - Clear intuitive website for sharing of valuable resources; repositories with growth potential - UConnect at UCAR’s Procedures - Google Sites - Social Media Strategy developed and reviewed - Curation – Internal - Curation – External Personal Priority 17. Help Spark work smarter and put the horse before the cart rather than vice versa and establish objective measures of product schedules, resources, and outcomes: Project Management Processes/tools in Spark for all development projects accessible via Google Site or Drupal-based (Scope Statement; audience; SWOT; procedural network diagram and Gantt charts; work breakdown structures; objective measures of performance and time allotment). |  |  |  |  |  |  |  |
| Product Description and Acceptable Criteria |  |  |  |  |  |  |  |
| Deliverable |  |  |  |  | Performance Targets/Tasks |  |  |
| A. Webcasts of stakeholder value will be streamed live, with the most valuable posted to the UConnect at UCAR YouTube channel |  |  |  |  | - calendar of live webcast events (confirmed w/ MMS) - MMS staff time to stream/capture video - need to improve production quality, platform - copyright agreement obtained in advance along with verbal contact with presenter to confirm compliance - Quarterly viewership report |  |  |
| B. Asynchronous archiving of selected webcasts on UConnect at UCAR’s YouTube channel and linked from UConnect Website |  |  |  |  | - notice (on calendar) when event is offered asynchronous - MMS time to capture video stream for archiving - time for webcast edits – copyright added - time to upload to UConnect YouTube for those presentations deemed of greatest value - Tags and metadata added to YouTube - Quarterly viewership report |  |  |
| C. Judicious selection of webinar delivery platform |  |  |  |  | - review and adapt based on budget constrains, new introduction to Google Apps and possible Hangout use - period of review and recommendation |  |  |
| D. Judicious selection of high-level webinars / Prep (see webinar checklist on UCU Google Docs) |  |  |  |  | - speakers confirmed and scheduled for 6-month period at least 30 days in advance (2 scheduling periods annually - Nov./Dec and July/August) - Calendar widely distributed 2x year - Website & registration form (email confirmation & notice & pre survey…) - Confirmation of roles: organizer; moderator; social media commenter; question facilitator; recorder - copyright clearance - Room scheduled for webinar and test - Training (w/ MMS) and Test (with Team) |  |  |
| E. Live Webinar |  |  |  |  | - Camtasia capture and audio recorder capture (See webinar checklist prepared from Webinar 1 & 2) - Evaluation - Quarterly viewership report, audience demographics |  |  |
| F . Asynchronous archiving of high-level webinars |  |  |  |  | - Add title slide - Add copyright slide - Needed edits in recording - Upload to YouTube UConnect Channel - Content, tags, metadata added - Quarterly viewership report/analytics |  |  |
| G. Video interviews providing QA with scientists -- in the spotlight (See production checklist, UConnect Google Docs) |  |  |  |  | - 6 month calendar (at least 30 days in advance) w/ scientists determined by editorial calendar and content need - Questions pre-determined by Spark and/or management team & provided to scientist in advance - Production check list - Room reservation and setup - Evaluation - Quarterly viewership/use report; analytics |  |  |
| H. Video repository development for media’s use |  |  |  |  | TBD based on specifications |  |  |
| I. Professionally produced videos, 8-10 annually, on topics of relevance and of value to our stakeholders |  |  |  |  | - 6 month Calendar w/ subject matter predetermined by management committee - Script: Spark written, w/ Comm and/or scientific review - Production COMET |  |  |
| J. Teaching Boxes, each summarized via a short video introduction, and placed in a meaningful context for K-12 educators |  |  |  |  | - Annual calendar (12-18) - content outlined; context video developed; templates - alignment to NGSS - test, review |  |  |
| K. Higher Ed Topical Teaching Boxes across key content areas and needs within the atmo- spheric sciences |  |  |  |  | - DPS model followed - Development of branded template - Development of “product” lists |  |  |
| - Clear intuitive website for sharing of valuable resources; repositories with growth potential |  |  |  |  | Planning, Wireframes through November Building, Testing – Dec. and January Updates, Maintenance Feb. on |  |  |
| M. UConnect at UCAR’s Procedures - Google UConnect at UCAR Site |  |  |  |  | Project Management Documents, Meeting Minutes, Website Wireframes, Website examples (design/content), Copyright forms, Calendars/Schedules, Webinar SME Considerations, Branding (logo, colors, web, YouTube, PPT, Webinar, video interview), Procedural checklists (webinar, production check list), How-to guides for content contributors and producers, Adherence to YouTube/Google/Vimeo/ requirements (ST), User/Community lists, Web 2.0 tools |  |  |
| N. Social Media tools for open and active site, commenting program plan established - TBD |  |  |  |  | - YouTube, Google+, posts to AtmosNews, Spark SciEd… - Rankings, commenting, community input |  |  |
| O. Curation - Internal |  |  |  |  | - Branded Template, 2014 |  |  |
| P. Curation – External resources |  |  |  |  | - Branded Template, 2014 |  |  |
| Q. Future Phases, Introduction TBD |  |  |  |  | - Training video portal w/ Comms, MMS - Virtual Field Trips (Polycom, Internet2) - Apps across institution - curation |  |  |
| CONSTRAINTS |  |  |  |  |  |  |  |
|  | Limitations |  |  |  |  |  |  |
|  | 1. Synergistic “advisory” team vs dedicated staff (labor) |  |  |  |  |  |  |
|  | 2. Budget |  |  |  |  |  |  |
|  | 3. Video expertise limited beyond PM |  |  |  |  |  |  |
|  | Needs |  |  |  |  |  |  |
|  | 1. Misc. resources that emerge (i.e. video storage) |  |  |  |  |  |  |
| 2. Funds/budget |  |  |  |  |  |  |  |
| 3. Web presence and website for internal PM |  |  |  |  |  |  |  |
| Assumptions |  |  |  |  |  |  |  |
| 1. Web engineer will be hired by November 15 with web presence available January 2014. |  |  |  |  |  |  |  |
| 2. Editorial calendar will be provided by November from Comms. or developed by UConnect Advisory Team by 11/15. |  |  |  |  |  |  |  |
| 3. Weather Channel involvement will be confirmed by January 1 along with mutually agreed upon deliverables, operating procedures, and standards. |  |  |  |  |  |  |  |
| TEAMS (suggested – not yet confirmed) |  |  |  |  |  |  |  |
| Community Webinars: Jeff Van Damme, MMS; Zhenya Gallon, Communications; Teri Eastburn, Spark; Cindy Schmidt, UCP |  |  |  |  |  |  |  |
| Career Mentorship Webinars: Rebecca Haacker Santos, Val Sloan, Bec Bathelor, Teri Eastburn, Stephanie Barr, Jeff Van Damme (MMS) |  |  |  |  |  |  |  |
| Webcasts: Jeff Van Damme & Staff, MMS; Teri Eastburn, Spark; Zhenya Gallon |  |  |  |  |  |  |  |
| Video Interviews: Teri Eastburn, Lisa Gardiner, Zhenya Gallon, Cindy Schmidt |  |  |  |  |  |  |  |
| UConnect at UCAR Website, 3rd Party Portals: Management Team oversite; Spark Web team |  |  |  |  |  |  |  |
| Teaching Boxes & Higher Ed: Lisa Gardiner – Lead; Teri Eastburn, Becca Hatheway, Randy Russell, Eileen Carpenter, Tim Barnes, Marc Muller |  |  |  |  |  |  |  |
| Video Productions: COE COMET (production); Scripting: Committee w/ scientific and UConnect/Spark Management Team review & appr approval. QA Production for education use: Teri + education team |  |  |  |  |  |  |  |
| Curation of UCAR assets: Staff contributed; Spark organized |  |  |  |  |  |  |  |
| Curation of select key outside assets: TBD – possibly initial curation is Spark’s responsibility followed by community contributions |  |  |  |  |  |  |  |
| Audiences |  |  |  |  |  |  |  |
| Higher Education, Member Universities |  |  |  |  |  |  |  |
| K-12 Educators |  |  |  |  |  |  |  |
| General Public/Media |  |  |  |  |  |  |  |
| Business & Government |  |  |  |  |  |  |  |
| Research Community |  |  |  |  |  |  |  |
| UCAR Staff |  |  |  |  |  |  |  |
| UCAR Management/Advisory Group |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |

My role:

Proactive on Program and Its Various Projects and commitment to program and project successes

Seek out information from those with insight (Emily, Mary, Karon, Kaye, Shawn

Develop Written and Detailed Plan with Advisory Committee, Management Input, Approval

Ensure Plan adherence

Involve key players as much as possible without budget support

Identify issues and risks, analyze them with advisory committee and elicit their support addressing them.

Communication – external and internal with advisory group, Spark, stakeholders, Management

Plan:  specific, measureable, aggressive, realistic, time sensitive

Calendars – communication, webcasts, webinars, video shorts QA, video stories, web

Schedule and Work Breakdown Structure

Key players: Establishing whom is needed, how much, and when

Determine TWC contribution and expectations

Online Project management tools to facilitate communication, matrics, and various analytics and other reports