My project is to develop a set of image calibration and analysis algorithms for a newly available Scientific CMOS (sCMOS) based array detector.  This detector is an integral part of a birefringent filter instrument being developed by NCAR’s High Altitude Observatory (HAO).  This instrument will be deployed to the Lomnicky Peak Observatory in Slovakia at the end of March 2011 where it will be interfaced to an existing 20cm coronagraph built by the Zeiss Corporation from Germany.  This unique instrument will make high resolution (5.5 megapixel images at the diffraction limit of the coronagraph), and high cadence (30 frames per second) observations of the entire solar corona between ~1.1 and 2 solar radii at wavelengths between 540nm and 1083nm.

This instrument will allow investigators to directly address two of the most important problems of the solar corona: (i) how is the solar corona heated and (ii) how and where do coronal mass ejections occur?  Both of these scientific questions require as basic data input, 2-D maps of coronal magnetic fields at high spatial resolution.  Furthermore, these magnetic fields are dynamic and high cadence measurements are required to resolve their changing structure.

Until recently, camera technology could provide either high resolution or high frame rates but not both in the same package and usually not with the low levels of noise required for scientific grade images of the corona. sCMOS technology, with its megapixel array size, 50 frames per second readout rates with a global shutter and 2-3 electrons of read noise, will provide a quantum leap in solar observation science if the technology produces on its promises.

I will specifically be accountable for image processing of sample data obtained from intended optical device, the PCO.EDGE sCMOS Camera. In order to interpret images and extract valuable data, they must first be processed to ensure there is minimal interference from noise and other pollution. This noise includes anomalies such as hot pixels, device defects, and aerosol inhibition from our atmosphere. Procedures to mitigate the impacts of these aforementioned defects include dark frame subtraction, flat field averaging, and correcting for aerosols. It is the intent that my work will promote the complete functional capabilities of this device to then be assembled within the intended coronagraph for optimum efficiency.

Week 1 – June 7-11

Deadlines: June 8th 12pm Work Plan and Literature Review due for Writing Workshop
Events: June 9th 8:45am FL2 Writing Workshop
Tasks: 
  	1. Utilize LabVIEW to create an algorithm capable of producing an AVI movie based on images collected from PCO.EDGE sCMOS Camera
    	2. Construct Prospectus for Writing Workshop

Week 2 – June 14-18

Deadlines: June 15th 12pm Prospectus due for Writing Workshop
                  June 15th 1pm Meeting with Raj
                  June 18th AVI Algorithm Due
Events: June 16th 845am FL2 Writing Workshop
             June 16th 10am FL2 Grad School Seminar
Tasks:
	1. Continue working with LabVIEW to program AVI movie
	2. Design Methods Section for Writing Workshop
Special Notes: Research Mentor will be out of town June 17-25

Week 3 – June 21-25

#### Deadlines: June 22th 12pm Methods Section due for Writing Workshop
Events: June 23th 845am FL2 Writing Workshop
             June 23th 10am FL2 AMS Policy Colloquium Seminar
Tasks:
	1. Commence utilizing LabVIEW for Dark Frame and Flat Field Corrections
           2. Commence initial considerations for upcoming practice talks
Special Notes: Research Mentor will be out of town June 17-25
		   I will be attending OU from June 24-26

Week 4 – June 28-July 2

Deadlines: July 2nd Dark Frame and Flat Field Corrections Due
Events: June 30th 8:45am FL2 Writing Workshop
             June 20th 10am FL2 Ethics in Science Seminar
Tasks: 
  	1. Continue using LabVIEW to perform dark frame and flat field corrections on images
	2. Prepare Practice Talk

Week 5 – July 5-9

Deadlines: July 7th Practice Talks
Events: July 5th HOLIDAY
             July 6th 9am FL1 Bring Your Self to Work Seminar
             July 6th Evening Dinner at Raj’s house
Tasks: 
  	1. Commence using LabVIEW to correct images for aerosol contamination

Week 6 – July 12-16

Deadlines: July 16th Aerosol Corrections Due
Events: July 12th 3pm Meeting with Rebecca
Tasks: 
  	1. Continue using LabVIEW to perform aerosol corrections to sample images
	2. Prepare Statement of Research Interests for Writing Workshop

Week 7 – July 19-23

Deadlines: July 19th Statement of Research Interests for Writing Workshop Due 
Events: July 22nd 8:45am UNAVCO Writing Workshop
             July 23rd Testing & Analysis of Sample Images Complete
Tasks: 
  	1. Finish any additional corrections that must be accounted for via LabVIEW
	2. Work on parts of paper not covered in Writing Workshop
	3. Construct Results and Discussions Section, and Revise Introduction for Writing Workshop

Week 8 – July 26-30

Deadlines: July 27th 12pm Results, Discussion, and Revised Introduction Sections due for Writing Workshop
                   July 29th Second Practice Talk
                   July 30th Abstracts Due
Events: July 28th 8:45am UNAVCO Writing Workshop
Tasks: 
  	1. Prepare for practice talk and oral presentation
	2. Prepare for Poster Session
	3. Prepare paper for final submission

Week 9 – August 2-6

Deadlines: August 2nd Colloquium Talks
                  August 5th Poster Session
                  August 6th Final Review
Tasks:
	1. Be relaxed, reflect on the wonderful summer, and give it my best shot