Our project is to develop a new type of coronagraph with the premise to better understand the heating of the corona. Current understanding of Earth’s temperature profiles cannot be applied to the corona due to deviations in composition and the vacuum of space in which the corona resides. I will specifically be accountable for image processing of sample data obtained from intended CCD device, the PCO.EDGE sCMOS Camera. In order to interpret images and extract valuable data, they must first be processed to ensure there is minimal interference from noise and other pollution. This noise includes anomalies such as hot pixels, device defects, and aerosol inhibition from our atmosphere. Procedures to mitigate the impacts of these aforementioned defects include dark frame subtraction, flat field averaging, and correcting for aerosols. It is the intent that my work will promote the complete functional capabilities of this device to then be assembled within the intended coronagraph for optimum efficiency.

Week 1 – June 7-11

Deadlines: June 8th 12pm Work Plan and Literature Review due for Writing Workshop
Events: June 9th 8:45am FL2 Writing Workshop
Tasks: 
  	1. Utilize LabVIEW to create an algorithm capable of producing an AVI movie based on images collected from PCO.EDGE sCMOS Camera
    	2. Construct Prospectus for Writing Workshop

Week 2 – June 14-18

Deadlines: June 15th 12pm Prospectus due for Writing Workshop
                  June 15th 1pm Meeting with Raj
                  June 18th AVI Algorithm Due
Events: June 16th 845am FL2 Writing Workshop
             June 16th 10am FL2 Grad School Seminar
Tasks:
	1. Continue working with LabVIEW to program AVI movie
	2. Design Methods Section for Writing Workshop
Special Notes: Research Mentor will be out of town June 17-25

Week 3 – June 21-25

#### Deadlines: June 22th 12pm Methods Section due for Writing Workshop
Events: June 23th 845am FL2 Writing Workshop
             June 23th 10am FL2 AMS Policy Colloquium Seminar
Tasks:
	1. Commence utilizing LabVIEW for Dark Frame and Flat Field Corrections
           2. Commence initial considerations for upcoming practice talks
Special Notes: Research Mentor will be out of town June 17-25
		   I will be attending OU from June 24-26

Week 4 – June 28-July 2

Deadlines: July 2nd Dark Frame and Flat Field Corrections Due
Events: June 30th 8:45am FL2 Writing Workshop
             June 20th 10am FL2 Ethics in Science Seminar
Tasks: 
  	1. Continue using LabVIEW to perform dark frame and flat field corrections on images
	2. Prepare Practice Talk

Week 5 – July 5-9

Deadlines: July 7th Practice Talks
Events: July 5th HOLIDAY
             July 6th 9am FL1 Bring Your Self to Work Seminar
             July 6th Evening Dinner at Raj’s house
Tasks: 
  	1. Commence using LabVIEW to correct images for aerosol contamination

Week 6 – July 12-16

Deadlines: July 16th Aerosol Corrections Due
Events: July 12th 3pm Meeting with Rebecca
Tasks: 
  	1. Continue using LabVIEW to perform aerosol corrections to sample images
	2. Prepare Statement of Research Interests for Writing Workshop

Week 7 – July 19-23

Deadlines: July 19th Statement of Research Interests for Writing Workshop Due 
Events: July 22nd 8:45am UNAVCO Writing Workshop
             July 23rd Testing & Analysis of Sample Images Complete
Tasks: 
  	1. Finish any additional corrections that must be accounted for via LabVIEW
	2. Work on parts of paper not covered in Writing Workshop
	3. Construct Results and Discussions Section, and Revise Introduction for Writing Workshop

Week 8 – July 26-30

Deadlines: July 27th 12pm Results, Discussion, and Revised Introduction Sections due for Writing Workshop
                   July 29th Second Practice Talk
                   July 30th Abstracts Due
Events: July 28th 8:45am UNAVCO Writing Workshop
Tasks: 
  	1. Prepare for practice talk and oral presentation
	2. Prepare for Poster Session
	3. Prepare paper for final submission

Week 9 – August 2-6

Deadlines: August 2nd Colloquium Talks
                  August 5th Poster Session
                  August 6th Final Review
Tasks:
	1. Be relaxed, reflect on the wonderful summer, and give it my best shot