AMS WeatherFest Timeline, 2013/2014

February: 	New Committee Members on board

Roles and Needs Solicited

SWAT of past weatherfest event and review of public and exhibitor surveys

March: 		Committee full and Roles/responsibilities confirmed

3 co-chairs; 3 others: local and national marketing, sponsorship, evaluation, workshop lead

Local chair(s) and local teacher rep determined

Confirmation of space for WeatherFest and space for Teacher Workshop (AMS)

April/May:	Subcommittees for WeatherFest Scholarship awards

Subcommittee for TeacherWorkshop Presenters/Agenda

June:		Website up-to-date with forms, applications, new video, correct info

Market Event via Atlanta “things to do” websites, papers

Teacher Workshop presenters solicitation up and actively sought online & diretly

Teacher Enrollment online and up and running

July:		Emcee and local entertainment sought and ideally confirmed for WeatherFest

August:		8/1 Deadline for Workshop Presenter Applications

September	Presenters notified for teacher workshop and acceptances/confirmations obtained

Regret letters sent to presenters not selected

Ribbon cutting selection and invitations

Secure Photographers and keep them in the loop re: event

Marketing to Teachers for Workshop

October		Updated exhibitor list -  Run 1

October 15 – 20th, WeatherFest Scholarship Rejection Letters out

Oct. 5-10, WeatherFest Scholarship Acceptance letters out

Travel information disseminated to scholarship recipients along with shipping info; store info; marketing info (think about what else you would want if you were new to it)

Nov.		Updated Exhibitor list – Run 2

Volunteer solicitations go out.  Ideal number is 40 at staggered times.

Door prizes solicited through exhibitors and informally from committee (letter sent)

Include in letter Survey Monkey survey pre and post event!!!!

Weather 101 Agenda confirmed

Teacher Workshop agenda fully confirmed

Local Marketing Plan ready to implement

Dec./Jan.	Mobile Phone numbers of key personal distributed.

Updated Exhibitor list – Run 3

Final Exhibitor List – posted online each year

Volunteer schedule developed, confirmed and disseminated

Weather Art Table volunteer support???

Snacks: popcorn, water (sponsor???)

Event:		Weather 101

Volunteers in action

Surveys for Exhibitors and Attendees

Passports and reward for children who participate

WeatherArt table

Floaters for booth awards

Door Prizes, Raffles

Hotel rooms are in place for WeatherFEst scholarship recipients (timing?)

Conference rooms or Convention Center rooms are reserved for teacher workshopsonline

draft a letter to be sent to former national WeatherFest participants and current Annual AMS Meeting exhibitors to see if they might be interested in WeatherFest participation. distribute to mailing list as appropriate.

- Door Prizes:  Jenn reiterated what was decided in the spring regarding door prizes:  colored paper in 3 colors approx. 2.875” x 2.125” for participants to put their names on.  We will have a drawing on the hour (1pm, 2pm, 3pm).  We have a spinner for the drawing already provided.  Teri will provide the paper “cards”, approximately 600 of each color. We should shoot for 12 door prizes that could include “Insider Tours” of local TV stations; the Austin Zoo; etc.  A letter will be written for WeatherFest participants to consider donating a door prize.  They should carry it with them to Austin and bring it to Jenn or Claudia before the event begins. (Teri will write the letter and Jenn will distribute it to participating companies/orgs.).

- The Passport was reviewed for use for students during Weather Fest.  It was decided that 1500 will be made available and that we will not involve the raffle in any way with the Passport.  Diffraction glasses will be given to those who participate with their passport.

- Teri reported that the blank cards are ready for the raffle.  She and Claudia both will bring pencils for those who’d like to participate in the raffle to write their information.

- Teri drafted a letter for door prizes that Jenn will send out to booth participants.  We are aiming to obtain 12.  There will be drawings at 1pm, 2pm, and 3pm, ideally from the representatives from the 3 weather stations that will be in attendance. Troy is scheduled for the first hour drawing.

- Grocery stores nearby