Minutes of the AMS Weather Fest Monthly Meeting

Tuesday August 6, 2013 1pm EST

Attending: Teri Eastburn, Claudia Gorski, Jen Sprauge, Hector Ibarra, Vivian Silva, Jenn Rosen, Eileen Carpenter

Next call will be Tuesday, September 3, 2013  1PM EST

WeatherFest Scholarship Application-Claudia

The WeatherFest scholarship application is online and posted on the teacher page. Claudia mentioned that some of the hotels are helping out with rooms, water and popcorn. These hotels include the Hyatt, Marriot and Westin. The Omni is not granting this service.

Teri suggested starting a list of people/hotels/others that will need to be thanked after the event. Sending thank you notes will be done and we will connect with the local participants in making sure that everyone involved is thanked accordingly.

Vivian suggested that we encourage the teachers involved with WeatherFest to attend the teacher workshop. Hopefully most of them will be informed of this opportunity and attend.

Teri will send Claudia some photos from WeatherFest 2012.

Jenn suggested that all forms be put online only and it was agreed that there would not be paper applications distributed.

Hector said Jen is working on the local contacts and will get back to Hector  (then Jennifer connected on the call and this topic was addressed).

Local Committee Report-Jen

Jen has reached out to Girl Scouts of greater Atlanta and they are very excited about being involved with WeatherFest. A pre WeatherFest Girl scout/Boy scout event (100 each) is planned. The plan is to have a rally in the morning, before the actual WeatherFest event, with Nick Walker, talk about local hazards and then divide the girls and boys for rotating groups. The timing for this could be 2 ½ - 3 hours. A trademark Weather Ready Nation patch will be available for both the Girl Scouts and Boy Scouts. The patch is part of a broader Weather Ready Nation program. The rotating groups will include requirements for the weather merit badge for both girls and boys. Tables topics would vary with examples being: making anemometer/emergency kits/learning about weather fronts. The students will break for WeatherFest and have a paper passport for which they can go to different booths to learn about different aspects of weather and get their passports stamped. When the Scouts complete the passport they can turn it into a Passport station and given written verification/proof of completion for their weather merit badge. Area coordinators have said they can help with this and there will be a shout out to volunteers for participation with this event.

Marketing

Teri suggested that the marketing plan be well organized and known to all so there will be continuity for all activities involved. The deadline for Corporate Booths/Teacher Booths might be extended. Jenn mentioned that is an average of 45-60 tables/booths at WeatherFest. We review the teacher booth applications but there is no process for corporation review.

We would like to see more people involved and the question of who to invite (brownies, certain ages of GS/BS) came up. We do not want to make the event restrictive. Jennifer responded and said we should not limit the age level for WeatherFest. The Boy Scout and Girl Scout organization will keep track of who is coming with their own pre-registration.  Girl Scouts will also market WeatherFest. They will need to make the distinction as to who can come at what time.

Vivian will set up a meeting with the local corporate participants to see what the topics will be at the booths. She will make sure that some of the participants address climate at their tables.

A teacher Sharathon is planned and visiting teachers might want to come to this.

The drop dead date for marketing is September 15th.

A big thank you was given to Jennifer for all the work she has done on organizing with the scouts and planning the patches/merit badge activities.

Teacher Workshop

Vivian suggested that we send reminders to people to have them forward the teacher workshop application to those that would be interested. The application is online.

The sponsor for the teacher workshop luncheon is 50% covered by UCAR. We need more funding for the luncheon and Scott at Viasala may provide the additional 50% needed. The Omni hotel is confirmed for the workshop with the deadline for applications being August 30th. Vivian will set up metrics for the teacher selection committee. Confirmation letters and accepting letters will be worked on after the deadline.

The teacher workshop presenters will need review in order to have the correct technology needed for their presentations. Vivian and Teri will put together a form for the presenters to fill out regarding needed equipment. The application does address this but making sure all is accurate is important. Claudia suggested adding a registration fee of $25.00 in order to cover the technology provided.

Registration for the teacher workshop is not up on the site yet. It will be online soon with the maximum number of teachers attending set at 50.  AMS can help getting word out about the workshop. There was a suggestion to get a PDF on the website to introduce teachers to the program. Vivian will work on this PDF. Vivian will also send Claudia a list of things needed for the workshop

Other

Everyone should think about a master of ceremonies for the event.

Teri will talk to locals, Chris and Susan, about coordinating the marketing for Ready Weather Nation and WeatherFest.

Chris will have a scholarship committee (of 3) to decide on teacher booth scholarships and is working on finalizing this. There will be 12 local teachers and 6 national teachers chosen for the scholarships.

Hector talked about the WeatherFest information form and that is available now on the website.

Teri and Vivian will do a teacher workshop agenda as soon as possible. Teri will ask the local participants (Chris S.) about marketing ideas that they have.

Teri wants to make sure that the people involved from last year have the opportunity to apply for scholarships.

Vivian is concerned that some people on the WeatherFest committee are not replying to emails and questioned the commitment to WeatherFest for some. She would like to see more regular involvement since there are important decisions to be made.

Action items:

-Contact Scott (Viasala) for sponsorship for the luncheon

-Add a $25.00 registration fee to presenters

-Work on PDF for website (Vivian)

-Put agenda for the teacher workshop up when we have one (Teri/Vivian)

-Continue communication to Scouts on local level (Jennifer)

-Coordinate marketing

-Send Claudia a list of what is needed from the hotel for the workshops

Call ended at 1:50PM EST, Next meeting is September 3, 2013, 1:00 EST