WeatherFest Committee Call

June 6, 2012

Attendees: Claudia Gorski, Jenn Rosen, Troy Kimmel, Kirsten Gurka, Jill Hasling, Steve Graham, Brent MacAloney, Teri Eastburn, Ron Gird, Mike Passow, Hector Ibarra

Opening Remarks/Co-Chairpersons: Teri Eastburn, Ron Gird

2:00–2:05 p.m. Local Committee Update: Troy Kimmel

Troy- Keep Austin Beautiful wants a volunteer to pick up materials on Friday and store them until Sunday.  Troy found a local volunteer to pick up supplies and deliver to venues on Sunday.  The Local Committee will begin contacting past WeatherFest participants from the last couple of events.  Troy met with Soutron and they are very interested in being a sponsor.  On Local Committee, a couple people have been tasked with finding sponsors for the teacher workshop.  The committee is also considering a few sponsorships for teachers.

Troy mentioned that Hector has been a big help in terms of potential scout, 4H, and other such organizations.  The event is expected to be 2 hours in length and should be done by 11:30 to allow completion before WeatherFest and those participating in the Flag ceremony. Hector noted that a consistent structure and agenda for this event each year would be very helpful in terms of planning. Troy noted that it will be PPT and web oriented, and will involve many of the local weather forecasters in Austin, including Bob Rose.

Brent-Local Committee is well ahead of where the other committees have been over the past five years, at this stage in the game.

Action: Troy and/or Hector to provide an agenda and confirm and schedule potential presenters for the scout workshop; room requirements and audio-visual needs to Jenn along with projected number that will attend (currently thought to be 50). (Troy will provide laptop; room will need screen, microphone, projector from AMS.)

2:05–2:10 p.m. Updates from AMS Headquarters: Jenn Rosen-Exhibits & Claudia Gorski – Meetings

The Website is up and ready and we already have one corporate application.  Application deadlines are a little earlier this year since the meeting is earlier in January. As she schedules booths, she tries to keep “like” types together (NOAA, those needing electricity, etc.)

Action: Claudia will reach out to the hotel and convention center about sponsorship over the next few weeks and will update on the next call.

2:10–2:20 p.m.   Teacher Workshop Update: Jill Hasling

Jill is trying to get sponsors and is working on preliminary outlines for the teacher workshop.  She is working on distributing information to teachers in the Education Dept in TX.  The Workshop will be held on Monday for K-8 and Tuesday (Jim Brey, AMS) for HS. This year, she is looking at the NWA model, which typically attracts 100 teachers during the work week.

Monday: K-8 , Tuesday: high school

Jill is trying to work closely with the University of TX and will also contact Texas science coordinators. Jill will focus on the workshop, which is a sure thing versus the entire AMS conference. Teachers’ workshop is free.  Registration fee would be required for the Education Symposium. EC budget would cover 100 people at the hotel and the Monday luncheon is sponsored by Earth Network.  In terms of the Jackson School event, Jill is looking in to any cost or transoportation sponsorship.  It was noted that if we require a nominal fee for teachers, past experience shows that we get a higher level of commitment from those who register to participate.

Action: Ron will send Jill a contact name for SR, possibly Walt Zaleski or Steven Cooper,

And will e-mail his contacts to find out how NWA gets teachers to commit.

Action: Claudia will talk to Keith about inclusion of teacher workshop participants in the 93rd AMS Conference.

Action: Jill to set deadline for planning purposes, for example, by October 1st, a number of teachers must be set.

Action: Jill to continue working on sponsorship.

Action: Jill to develop the application.

2:20–2:30 p.m.  Review of Committee Assignments

All-team participation

See wiki Web site: https://wiki.ucar.edu/display/wxfest/Roles+and+Responsibilities

Brent mentioned the idea of distributing passports to kids so they can visit some of the participating booths and get stamps on the passports.  Jen stated that, in the past, issues with timing and funding have prevented this from coming to fruition.

Action: Brent will spearhead the effort and the design of the passport.

2:30–2:40 p.m.  Teacher Funding Application Review Committee

Teri is leading effort.  Ron volunteered to review apps.  Teri would like to have four reviewers total.  Jen will collect apps as they come in for teachers and corporations.  Once the application deadline passes, Jen can upload them to the wiki or upload to an internal AMS site.  Teri and Jen to discuss offline.  Deadline for apps is 9/15.  Teachers will be notified by mid-October.  AMS usually receives 15-20 apps for 12 slots.  They have funding for12 local participants or 8 national participants.

Action: Teri and Jenn to determine where applications should be held.

Action: Teri to contact members of the BOPE board to recruit two additional

individuals for the Teacher Funding Application Review committee.

2:50–2:55 p.m.  Set Schedule for future Weather Committee meetings

Will try to shoot for second Wednesday of every month.

Action: Teri will send out a Doodle poll for next month’s meeting.

2:55–3:00 p.m.  "Once around the bases" – Last Call item

300pm--meeting adjourned